## Sprint 1 Task Tracker
Navigator — Sprint 1 Project Tracker
Data Extraction, Annotation & Validation Set Build ¦ Jul 28 – Aug 11, 2026
Task ID | Phase | Task | Owner | Start Date | Due Date | Duration (days) | Status | Priority | Dependencies | Notes
T01 | Corpus Intake | Export conversation threads from source system | Michael | 2026-07-28 | 2026-07-29 | 2 | Not Started | P0 | — | Deliver as JSON or CSV to data-pipeline/raw/
T02 | Corpus Intake | Review raw corpus format and write intake parser | Navigator | 2026-07-28 | 2026-07-30 | 3 | Not Started | P0 | T01 | Output: data-pipeline/src/intake.py
T03 | Privacy & PII | Run automated PII scan (regex + Presidio) | Navigator | 2026-07-30 | 2026-07-31 | 2 | Not Started | P0 | T01 | Flag all turns where pii_present=True
T04 | Privacy & PII | Manual review of PII-flagged turns | Michael | 2026-07-31 | 2026-08-01 | 2 | Not Started | P0 | T03 | Approve redaction or exclude
T05 | Privacy & PII | Apply redaction pass and export clean corpus | Navigator | 2026-08-01 | 2026-08-02 | 2 | Not Started | P0 | T04 | Output: data-pipeline/processed/clean_corpus.jsonl
T06 | Annotation | Run calibration session (20-turn calibration set) | Navigator + Michael | 2026-08-02 | 2026-08-03 | 2 | Not Started | P0 | T05 | Establish baseline inter-rater agreement
T07 | Annotation | Annotate first 1,000 turns (Train batch 1) | Navigator | 2026-08-03 | 2026-08-06 | 4 | Not Started | P0 | T06 | Target exemplar_quality ≥ 3 for all
T08 | Annotation | Inter-rater reliability check (Cohen's Kappa) | Navigator | 2026-08-06 | 2026-08-07 | 1 | Not Started | P0 | T07 | Gate: Kappa ≥ 0.70 per dimension
T09 | Annotation | Remediate low-confidence turns (confidence=1) | Navigator | 2026-08-07 | 2026-08-08 | 2 | Not Started | P1 | T08 | Re-annotate flagged turns
T10 | Dataset Build | Stratified split (Train/Val/Test/Human-Eval) | Navigator | 2026-08-08 | 2026-08-09 | 2 | Not Started | P0 | T07 | 70/10/10/10 per schema
T11 | Dataset Build | Format splits to JSONL (chat_completion format) | Navigator | 2026-08-09 | 2026-08-10 | 2 | Not Started | P0 | T10 | Output: data-pipeline/splits/*.jsonl
T12 | Dataset Build | Run schema validation CI check | Navigator | 2026-08-10 | 2026-08-10 | 1 | Not Started | P0 | T11 | All splits must pass validate_schemas.py
T13 | Dataset Build | Export human-eval set (sealed, separate folder) | Navigator | 2026-08-10 | 2026-08-11 | 1 | Not Started | P0 | T11 | Never used in training; access-controlled
T14 | Sprint Review | Sprint 1 review and Sprint 2 readiness gate | Michael + Navigator | 2026-08-11 | 2026-08-11 | 1 | Not Started | P0 | All | Check: corpus size ≥ 1,000 annotated turns; Kappa ≥ 0.70; 0 PII leaks
T15 | Sprint Review | Update README and merge sprint/1 to main | Navigator | 2026-08-11 | 2026-08-11 | 1 | Not Started | P1 | T14 | Tag release: v0.2.0-sprint1
SUMMARY | Total Tasks: 15 | P0 Tasks: 12 | P1 Tasks: 3 | P2 Tasks: 0 | Sprint Duration: 14 days | Jul 28 – Aug 11, 2026

## Corpus Intake Checklist
Corpus Intake Checklist — Sprint 1
Complete before T01 due date (Jul 29) — Owner: Michael
# | Requirement | Format / Detail | Status | Notes
1 | Conversation export format | JSON or CSV with fields: conversation_id, turn_id, user_message, model_response, timestamp | ☐
2 | Minimum corpus size | At least 1,500 turns for Sprint 1 annotation batch | ☐
3 | Conversation diversity | Includes at least 3 of: code requests, planning, research, explanation, clarification turns | ☐
4 | No pre-existing PII | Do a first-pass review before delivering; Navigator will do a second automated pass | ☐
5 | Timestamps present | ISO 8601 format preferred | ☐
6 | Outcome signals (optional) | Follow-up messages, ratings, or thumbs up/down if available | ☐
7 | Source system identified | Note which system the conversations came from (e.g., Copilot, GPT-4, internal) | ☐
8 | Delivery location | Drop files to: D:\AI-Hub\Knowledge\Inbox\sprint1-corpus\ | ☐
9 | Access granted to Navigator | Shared or copied to agreed working location | ☐
10 | Michael sign-off | Confirm corpus is ready for intake | ☐
Sprint 1 Acceptance Criteria
Gate | Criterion | Target | Status | Notes
S1-G1 | Annotated turns in Train split | ≥ 1,000 | ☐ | Minimum for viable Sprint 2 finetune
S1-G2 | Inter-rater Cohen's Kappa (all dims) | ≥ 0.70 | ☐ | Required for annotation quality
S1-G3 | PII leak rate in clean corpus | 0.00% | ☐ | Zero tolerance
S1-G4 | Exemplar quality avg (Train) | ≥ 3.2 / 5.0 | ☐ | Minimum quality bar
S1-G5 | Schema validation pass rate | 100% | ☐ | All JSONL records valid against schema

## Annotation Log
Sprint 1 — Annotation Progress Log
Running log updated daily ¦ Target: 1,000 turns annotated by Aug 6, 2026
SPRINT SUMMARY
Target Turns: | 1,000 | Days Allocated: | 4 (Aug 3 – Aug 6) | Required Daily Pace: | 250 turns / day | Kappa Gate: | ≥ 0.70
Date | Annotator | Turns Completed (Today) | Cumulative Total | % of Target | Kappa (Latest) | Issues Flagged | Notes
2026-08-03
2026-08-04
2026-08-05
2026-08-06
Target | — | — | 1000 | 100% | ≥ 0.70 | — | Sprint 1 gate